## Example risk register
CONSTRUCTION RISK REGISTER EXAMPLE
|  | Enter Risk Category titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. |  |  |  | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION (INCLUDING IF / THEN STATEMENT) | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | LIKELY TIMING OF RISK | RISK TRIGGER | MITIGATION / RESPONSE PLAN | STATUS OF MITIGATION / RESPONSE | OWNER | OTHER NOTES
10001 | MM/DD/YY | Materials | If there are changes in architectural plans that require additional or different resources, then there will be delays. | 1 | 8 | 8 | The risk is present throughout the process of finalizing architectural plans. | There are changes in the architectural plans. | A designated team member will continually monitor any proposed changes in architectural plans and ensure communication between architectural and construction teams about proposed changes. | No current issues | Joe Smith; architectural liaison
10002 | MM/DD/YY | Contracts | If contractual issues among contractors, subcontractors, or vendors arise, then there will be delays or cost overruns. | 2 | 4 | 8 | The risk is present before most contract work commences. However, the risk will also be present when additional contracts are added in the early phases of construction. | The contracts manager reports any potential contract issues. | The contracts manager will continually monitor contracts, alert the team when there are issues, and ensure that the team addresses and resolves contract issues before they cause delays. | Working on one unresolved issue with the electrician's contract; meeting set for May 2nd | Sue Johnson, contracts manager
10003 | MM/DD/YY | Permits / Regulations | If obtaining appropriate construction permits takes longer than planned, then there will be delays. | 2 | 8 | 16 | The risk is present throughout the construction phase of the project, including when securing required permits at the beginning of construction. | Construction permits do not arrive within the required timeframe. | The construction manager, or another designated team member, will monitor the project schedule and deadlines and ensure that all permits can accommodate the project's construction schedule. | All deadlines currently being monitored | Dale Swenson, construction manager
10004 | MM/DD/YY | Construction Site | If unexpected hazardous waste is found on the property, it will require mitigation or cleanup. | 1 | 8 | 8 | The risk is present throughout the project, especially toward the beginning when conducting site preparation work. | On-site managers report an issue, especially during site preparation. | The construction manager will assign a team member to monitor and explore any possible issues with hazardous waste. | No issues found to this point | Jeff Baker, construction assistant
|  |  |  | 1 | 1 | 1
|  |  |  | 1 | 2 | 2
|  |  |  | 1 | 4 | 4
|  |  |  | 1 | 8 | 8
|  |  |  | 1 | 16 | 16
|  |  |  | 2 | 16 | 32
|  |  |  | 3 | 16 | 48
|  |  |  | 4 | 16 | 64
|  |  |  | 5 | 16 | 80

## BLANK - Risk Reg
PROJECT RISK REGISTER TEMPALTE
|  | Enter Risk Category titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. |  |  |  | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION (INCLUDING IF / THEN STATEMENT) | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | LIKELY TIMING OF RISK | RISK TRIGGER | MITIGATION / RESPONSE PLAN | STATUS OF MITIGATION / RESPONSE | OWNER | OTHER NOTES
10001 | MM/DD/YY | Project Management | If group members do not complete tasks on time, then the project may fall behind schedule and miss deadlines. | 4 | 8 | 32 | During all iterations | Tasks overdue or incomplete GitHub commits | Use weekly meetings, assign clear responsibilities, and track progress using GitHub boards and the Gantt chart. | Monitoring progress weekly | Charlie, Project Manager
10002 | MM/DD/YY | Technical | If GitHub merge conflicts occur, then important website code may be overwritten or lost. | 3 | 16 | 48 | Iteration 3 integration stage | Multiple users editing the same file | Make sure each member works on separate branches, regularly commits changes, and tests merges before pushing to main branch. | Preventative actions in place | Jordan Smith, lead developer
10003 | MM/DD/YY | Testing | If website pages are not tested correctly, then users may experience broken links or missing content. | 3 | 8 | 24 | Before final deployment | Errors discovered during user testing | Complete manual user acceptance testing and record issues for correction before publishing. | User testing scheduled | Taylor Brown, QA test lead
10004 | MM/DD/YY | Communication | If communication between group members is unclear, then tasks may be duplicated or missed. | 4 | 4 | 16 | Throughout project | Missed meetings or unclear instructions | Hold regular meetings, record meeting minutes, and communicate through agreed channels such as Discord. | Ongoing | Group members, communication team
10005 | MM/DD/YY | Deployment | If GitHub Pages deployment fails, then the website may not be accessible for assessment submission. | 2 | 16 | 32 | Final publishing stage | Website does not load correctly online | Test GitHub Pages deployment early and confirm all files are linked correctly before final submission. | Monitoring deployment | Alex Wilson, technical lead
10006 | MM/DD/YY | Resource | If a group member becomes unavailable, then project tasks may not be completed on time. | 2 | 8 | 16 | Any stage of project | Lack of communication or absence | Share workload evenly and ensure all members understand each task so work can be reassigned if needed. | Backup plan prepared | Josh, team leader
10007 | MM/DD/YY | Quality | If uploaded HTML files contain coding errors, then the website may not function correctly. | 3 | 8 | 24 | During coding and integration | Errors found in browser testing | Review code before merging and validate website functionality after each update. | Code reviews ongoing | Jordan Smith, web developer
10008 | MM/DD/YY | Security | If repository permissions are incorrect, then files may be accidentally deleted or edited. | 2 | 4 | 8 | Throughout development | Unexpected file changes or deletions | Restrict repository access to project members only and regularly back up project files. | Permissions checked | Cameron, repository owner
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Dropdown Keys – DO NOT DELETE –
PROJECT RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80
PROBABILITY KEY | IMPACT KEY
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16
Enter Risk Category titles below to populate the Risk Register Dropdown Menu.
RISK CATEGORY
Project Management
Technical
Testing
Communication
Deployment
Resource
Quality
Security
Category Nine
Category Ten
PROBABILITY
IMPACT